## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | TA Profile Creation | As a TA applicant, I want to create and save my personal profile, so that I can provide my information for job applications. | Must Have | Iteration 1 | 1. TA can input profile info. 2. Profile is saved to file. 3. Profile can be re-opened. | 5 | Core TA function | 2026-03-09 | 2026-03-22
2 | TA Upload CV | As a TA applicant, I want to upload my CV file, so that MOs can review my experience. | Must Have | Iteration 1 | 1. TA can select and upload a file. 2. File path/name is recorded.. | 3 | File storage practice | 2026-03-09 | 2026-03-22
3 | TA Browse Jobs | As a TA applicant, I want to browse all available jobs, so that I can find suitable positions. | Must Have | Iteration 1 | 1. Job list is displayed clearly. 2. Jobs can be viewed in full | 5 | Core job discovery | 2026-03-09 | 2026-03-22
4 | TA Apply for Jobs | As a TA applicant, I want to submit applications for open jobs, so that I can be considered by MOs | Must Have | Iteration 2 | 1. TA can apply for one or more jobs. 2. Application is saved successfully | 5 | Core application flow | 2026-03-23 | 2026-04-12
5 | MO Post Jobs | As a Module Organiser, I want to create and publish job posts, so that I can recruit TA | Must Have | Iteration 2 | 1. MO can fill job details. 2. Job is visible to applicants | 5 | Core MO function | 2026-03-23 | 2026-04-12
6 | MO Select Applicants | As a Module Organiser, I want to view and select applicants, so that I can hire suitable TAs. | Must Have | Iteration 2 | 1. MO can view applicant list. 2. MO can mark selected applicants | 5 | Core hiring flow | 2026-03-23 | 2026-04-12
7 | Admin Monitor Workload | As an Admin, I want to view TA workloads, so that I can prevent overallocation. | Must Have | Iteration 3 | 1. Admin can view workload summary. 2. Data is loaded from files | 3 | Admin management | 2026-04-13 | 2026-05-10
8 | TA Application Status | As a TA applicant, I want to view my application status, so that I know the result. | Should Have | Iteration 3 | 1. Status shows: Pending/Selected/Rejected. 2. Status updates correctly | 5 | Usability improvement | 2026-04-13 | 2026-05-10
9 | AI Skill Matching | As an Admin, I want the system to suggest balanced workload allocation, so that TAs are not overloaded.. | Should Have | Iteration 4 | 1. System shows matching score/list. 2. Logic is explainable | 8 | AI-assisted feature | 2026-05-11 | 2026-05-24
10 | AI Workload Balancing | As an MO/TA, I want the system to match skills between jobs and applicants, so that recruitment is more efficient. | Could Have | Iteration 4 | 1. System gives allocation suggestions. 2. Results are explainable. | 8 | Optional AI feature | 2026-05-11 | 2026-05-24